## Timeline
S/No. | Activity | Duration (Working Days) | Start Date | End Date | Status
1 | Awareness Workshop on RTSIS Project | NA | 2021-11-01 | 2022-02-01 | Completed
2 | Sharing of a draft API Specification Documents to FSPs | 5 |  |  | Completed
3 | FSPs review and comments on a draft API Specification Document | 30 |  |  | Completed
4 | Workshop on RTSIS Data Collection API Specification | 2 | 2022-11-10 | 2022-11-11 | Completed
5 | Sharing of a final API Specification Documents to FSPs | 5 | 2023-01-09 | 2023-01-13 | Completed
6 | Development of API based on RTSIS API Specification Documents | 120 | 2023-01-16 | 2023-05-19 | On going
7 | Integration test of RTSIS API | 20 | 2023-05-01 | 2023-08-31 | On going
8 | User Acceptance Tests | 20 | 2023-10-01 | 2023-11-30 | Open